## Objective (hidden)
Objective 1: Lead customer enablement initiatives to drive adoption of digital making solutions | KR1: Develop and publish project-based tutorial that showcases how to use Cytron products effectively in real-world applications. KR2: Organize and improve access to Cytron tutorials by enhancing content discoverability on the website or others platform
Objective 2: Co-create and lead the development of high-impact technical marketing content | KR1: Develop technical project that aligned with current trends or popular use cases to boost content engagement and viewer interest
Objective 3: Enable internal teams and improve customer experience by delivering scalable technical tools, actionable insights, and strategic event participation. | KR1: Create and provide reusable technical assets (demo kits, documentation, templates) that internal teams can use to promote and sell Cytron products more effectively KR2: Participate in customer-facing event to gather feedback and share actionable recommendations with the teams

## Q3 Done (hidden)
Objective 1: Lead customer enablement initiatives to drive adoption of digital making solutions | KR1: Develop and publish project-based tutorial that showcases how to use Cytron products effectively in real-world applications. | 1. Getting Started with Cytron Motor Driver (4 Sub Tutorial) 2. Huskylens with Arduino 3. Revise previous tutorial (getting started arduino, motor driver, dll)
| KR2: Organize and improve access to Cytron tutorials by enhancing content discoverability on the website or others platform | 1. Active Cytron Tutorial (https://docs.google.com/spreadsheets/d/1_Ccb6zWsSKEKIJvoa_kkTkIClYfCiIxLpb4rbwO6iZc/edit?usp=sharing) 2. Tutorial Thumbnail Standardize (https://www.canva.com/design/DAGwBiQ9QlU/Z09yd5_2ps12UwbcYKkCdA/edit?utm_content=DAGwBiQ9QlU&utm_campaign=designshare&utm_medium=link2&utm_source=sharebutton) 3. Tutorial Workflow Plan (https://www.canva.com/design/DAGxaY_1Iz0/5drDFJEBKUuW8ij7SEG_dw/edit?utm_content=DAGxaY_1Iz0&utm_campaign=designshare&utm_medium=link2&utm_source=sharebutton) 4. Brand Strategy: Tutorial Landing Page: Homepage Mockup (https://www.canva.com/design/DAGtYo76Nj4/QUYFolrYxorMBctXQVP0Og/edit?utm_content=DAGtYo76Nj4&utm_campaign=designshare&utm_medium=link2&utm_source=sharebutton) 5. Cytron Tutorial Template (https://docs.google.com/document/d/1JfWwiPO1W03pD32-JeDY3Nln6BtZBDrpd47TfP4Habc/edit?usp=sharing)
Objective 2: Co-create and lead the development of high-impact technical marketing content | KR1: Develop technical project that aligned with current trends or popular use cases to boost content engagement and viewer interest | 1. Soccer Robot with Sumo:Bit 2. FireFighting Robot with Motion 2350 3. AI Robot using Huskylens with Motion 2350 Mobile Robot 4. Sumo Robot with Maker Uno RP2040 + MD13S
Objective 3: Enable internal teams and improve customer experience by delivering scalable technical tools, actionable insights, and strategic event participation. | KR1: Create and provide reusable technical assets (demo kits, documentation, templates) that internal teams can use to promote and sell Cytron products more effectively | 1. RDK Robot Kit (https://docs.google.com/spreadsheets/d/1lo0MsWwMF7XKLuT5jSoVzWqCGzBPNfDhgvnaYozxjFo/edit?usp=sharing) 2. Sumo Robot Improvement with Ikedo Kogeki 3. Testing Creality Hi Combo 3D Printer (https://docs.google.com/spreadsheets/d/1urEnwTPikZRccEe8PG-0Sp95xkslWJx_BaGRJ-s975I/edit?usp=sharing) 4. Sumo Robot Workshop Slide (https://docs.google.com/presentation/d/16HU2KqVxUEeF8GCwZrZ-7fOqqe7-J_tlHYuCJoGXsAU/edit?usp=sharing) 5. 3D Printer Workshop (Bambu Lab) Slide (https://docs.google.com/presentation/d/1vvWWy_2jWwpxU5PnkhBS_oCZnyQYNJHjDd7TF5Se0VI/edit?usp=sharing)
| KR2: Participate in customer-facing event to gather feedback and share actionable recommendations with the teams | 1. Robomania 2. 3D Printer Workshop at Politeknik Sultan Idris Shah 3. Sumo Robot Bengkel at SK Arau 4. IIUM Robotic Competition (IRC) at IIUM Gombak 5. RAC Final at Nilai University (as Chief Judge Rero Micro) 6. AI Horizon at SPICE Penang

## Q4 Plan
OBJECTIVE | KEY RESULTS | ACTION PLAN | Reference Link | Q4 Recap
Objective 1: Take ownership of the Cytron Tutorial platform to ensure it is well-organized, updated, and user-friendly | KR1: Audit and standardize all tutorials to improve structure and consistency, enhance layout for better usability, and align topics with new products and trends | 1. Audit and categorize all existing tutorials to identify outdated or duplicate content. Will find the missing gap on all cytron tutorial using Active Cytron Tutorial | Active Cytron Tutorial | Total 1347 Tutorial (Until August 2025) 162 Disable, 100+ Updated
|  | 2. Standardize format and visuals (titles, cover images, tags, structure) for consistent presentation. Ask help from Creative or Marketing team to create standardize thumbnail for future tutorial. For previous tutorial just follow the, Tutorial Thumbnail Standardize | Active Cytron Tutorial | Done make standardize for Motor Driver, NVIDIA, IRIV, Arduino (On Progress), etc
|  | 3. Continue finished up previous progress on Tutorial Workflow Plan | Tutorial Workflow Plan
4. For tutorial landing page or homepage, we will separate news from the list of tutorial. The news section can be utilize by others team such as Iffah or Industry Team. (On Going)
|  | 5. Make special telegram group to organize all the tutorial write including trainee. Make sure all the writer follow the Cytron Tutorial Template | Cytron Tutorial Template
|  | 6. Start discovering Documentation or Guide for Industry Product |  | Done Restructuring All Industrial Tutorial related
Objective 2: Develop high-impact tutorials that enhance user experience and reduce repeated customer inquiries | KR1: Create new tutorials that address common user issues, reduce repetitive support requests, and gather feedback to continuously improve content quality. | 1. Write all Cytron Motor Driver getting started | Cytron Motor Driver | Done cover almost of our Cytron Motor Driver
|  | 2. RDK's Project to fill the gap on Tertiary Area. | RDK's Project | 5 ROS Project, Launched RDK AI Robot Kit
3. Analyze customer support inquires and FAQs to identify common questions or recurring issues. Will work together with Solehin for customer inquiries in Telegram Group.
Objective 3: Collaborate with other teams to strengthen Cytron’s capability in 3D Printing, Robotics, and STEM initiatives | KR1: Support cross-team projects and develop demo resources that highlight Cytron’s technical strengths in 3D Printing, Robotics, and STEM areas | 1. Engage with Education, Ecodev, and Marketing teams to identify ongoing or upcoming projects in 3D Printing, Robotics, and STEM.
2. Join relevant events or workshops to gather direct feedback from users and showcase Cytron’s technical strengths
3. Share insights from these activities to help refine future products or content.
Incoming Task/Event 1. Review and test for Creality K2 Pro 3D Printer compared to Bambu Lab P1S 2. Digital Carnival @ SSTP on 2-4 November 3. PISF 2025 on 8-9 November 4. RAC2026 (as comittee) starting Mid October
|  | Next Event if needed 1. Bengkel Asas Sumo Robot 2. 3D Printer Workshop |  | 3D Printer workshop at UniMap

## Gannt Chart Q4
|  |  | October |  |  | November |  |  |  | Disember
|  | 6hb - 10hb | 13hb - 17hb | 20hb - 24hb | 27hb - 31hb | 3hb - 7hb | 10hb - 14hb | 17hb - 21hb | 24hb - 28hb | 1hb - 5hb | 8hb - 12hb | 15hb - 19hb | 22hb - 26hb | 29hb - 2hb
Objective 1: Take ownership of the Cytron Tutorial platform to ensure it is well-organized, updated, and user-friendly | 1. Special Telegram Group for All Cytron Tutorial Writer
2. Cytron Tutorial Template (Merge with WI from Athirah)
3. Update status for all tutorial
4. Start disable for discontinued item
5. List out all the categories (Based on Thumbnail)
6. Setup design for thumbnail (Ask help from Creative/Marketing)
7. Update Thumbnail for Relavant Tutorial
8. Update Product Link for Relavant Tutorial
9. Update Community Banner
10. Plan schedule for Personal Social Media posting
| 11. Scrap tutorial data for early August to end of November | [7 empty] | Refer Ecodev
| 12. Internal Training for Tutorial Writers | [8 empty] | Next January
13. Assign Trainee for Re-Edit relavant tutorial
14. Monitor and work as editor for latest tutorial
Objective 2: Develop high-impact tutorials that enhance user experience and reduce repeated customer inquiries | 1. Getting Started With FD04A Using Arduino (re-edit)
2. Discovering about EdgeAI Tutorial
3. MD10-POT: Controlling DC Motor without Code (re-edit)
4. Let’s Arduino Control Your SmartDriveDuo-10 (re-edit)
5. Getting Started with Arduino and Blynk
5. SmartDrive40 Using 3.3V Microcontroller (re-edit)
6. Let's Arduino Control Your SmartDriveDuo-60 (re-edit)
7. Getting Started with 3A Motor Driver Shield and Arduino Uno
8. HAT-MDD10
9. SHIELD-MDD10
10. MD25HV
11. Reserve for another hot topic tutorial
12. Reserve for another hot topic tutorial
Objective 3: Collaborate with other teams to strengthen Cytron’s capability in 3D Printing, Robotics, and STEM initiatives | 1. 1st RAC2026 Committee Discussion
2. Review Creality K2 Pro Combo
| 3. Soccer 4WD rev2 | [8 empty] | Change to Soccer:bit
| 4. Techdome Soccer Robot Special Request | [8 empty] | Postpone to Q1
| 5. Karnival MSN 2025 Zon Utara |  |  |  | 25-27 Oct
| 6. Digital Carnival @ SSTP |  |  |  |  | 2-4 Nov
| 7. PISF 2025 | [5 empty] | 8-9 Nov
8. Edu Pico 2 Reviewer
9. Soccer:Bit
10. 3D Printer Workshop at Unimap
10. RAC Gameplay Discussion (18 Dec)
11. Reserve for ad-hoc event or task from another department
ACTUAL
Objective 1: Take ownership of the Cytron Tutorial platform to ensure it is well-organized, updated, and user-friendly | Special Telegram Group for All Cytron Tutorial Writer
Cytron Tutorial Template (Merge with WI from Athirah)
Update status for all tutorial
Start disable for discontinued item
List out all the categories (Based on Thumbnail)
Setup design for thumbnail (Ask help from Creative/Marketing)
Update Thumbnail for Relavant Tutorial
Update Product Link for Relavant Tutorial
Plan schedule for Personal Social Media posting
Cytron Tutorial Learning Pathway (Arduino)
Cytron Tutorial Learning Pathway (Raspberry Pi)
Daily Posting (Telegram Group)
Automation for Tutorial
IRIV Series Learning Path
Objective 2: Develop high-impact tutorials that enhance user experience and reduce repeated customer inquiries | Verify all Cytron Motor Driver Tutorial
Getting Started With MDD3A/MAKER DRIVE Using Arduino
Getting Started With FD04A Using Arduino
Start Discovering about EdgeAI Tutorial
MD10-POT: Controlling DC Motor without Code (re-edit)
Let’s Arduino Control Your SmartDriveDuo-10 (re-edit)
Getting Started with Arduino and Blynk
SmartDrive40 Using 3.3V Microcontroller (re-edit)
Let's Arduino Control Your SmartDriveDuo-60 (re-edit)
Getting Started with 3A Motor Driver Shield and Arduino Uno
Revamp Raspberry Pi 400 Tutorial (Makers Bundles)
Revamp WS2812 Ring Tutorial (Makers Bundles)
Revamp DIY Table Lamp with Neopixel strip Tutorial (Makers Bundles)
Revamp Display Images on Graphic LCD with Maker Nano RP2040
Revamp Displaying Telegram Message on Dot Matrix Using Raspberry Pi
Revamp IoT-Based Door Security Alarm System Using Pico W and Telegram
Getting Started with Arduino Uno (Revamp)
Soccer Robot using SUMO:BIT
Getting Started with 3D Printed ZOOM:BIT
Objective 3: Collaborate with other teams to strengthen Cytron’s capability in 3D Printing, Robotics, and STEM initiatives | Creality HI Combo vs Bambu Lab A1 Combo
Review Creality K2 Pro Combo
RAC2026 Committee Discussion
Karnival MSN 2025 Zon Utara
Soccer 4WD rev2
Digital Carnival @ SSTP
Repair Bambulab P1S (Production) - 3 unit
PISF 2025
EDU PICO Workshop @ UiTM PP - 12 Nov
CES Campaign (Price Drop)
EDU PICO 2 Book Reviewer
CES Campaign (Maker Box)
CES Campaign (Maker Bundless)
CES Campaign (Tiktok Live)
JPNPP STEM Grooming Camp
3D Printer Workshop at Unimap (10/12)
Soccer:Bit (Re-edit from 4WD Soccer)
3D Printed ZOOM:BIT

## Q1 Plan
OBJECTIVE | KEY RESULTS | ACTION PLAN | Reference Link | Q4 Recap
Objective 1: Take ownership of the Cytron Tutorial platform to ensure it is well-organized, updated, and user-friendly | KR1: Audit and standardize all tutorials to improve structure and consistency, enhance layout for better usability, and align topics with new products and trends | 1. Audit and categorize all existing tutorials to identify outdated or duplicate content. Will find the missing gap on all cytron tutorial using Active Cytron Tutorial | Active Cytron Tutorial | Total 1347 Tutorial (Until August 2025) 162 Disable, 100+ Updated
|  | 2. Standardize format and visuals (titles, cover images, tags, structure) for consistent presentation. Ask help from Creative or Marketing team to create standardize thumbnail for future tutorial. For previous tutorial just follow the, Tutorial Thumbnail Standardize | Active Cytron Tutorial | Done make standardize for Motor Driver, NVIDIA, IRIV, Arduino (On Progress), etc
|  | 3. Continue finished up previous progress on Tutorial Workflow Plan | Tutorial Workflow Plan
4. For tutorial landing page or homepage, we will separate news from the list of tutorial. The news section can be utilize by others team such as Iffah or Industry Team. (On Going)
|  | 5. Make special telegram group to organize all the tutorial write including trainee. Make sure all the writer follow the Cytron Tutorial Template | Cytron Tutorial Template
|  | 6. Start discovering Documentation or Guide for Industry Product |  | Done Restructuring All Industrial Tutorial related
Objective 2: Develop high-impact tutorials that enhance user experience and reduce repeated customer inquiries | KR1: Create new tutorials that address common user issues, reduce repetitive support requests, and gather feedback to continuously improve content quality. | 1. Write all Cytron Motor Driver getting started | Cytron Motor Driver | Done cover almost of our Cytron Motor Driver
|  | 2. RDK's Project to fill the gap on Tertiary Area. | RDK's Project | 5 ROS Project, Launched RDK AI Robot Kit
3. Analyze customer support inquires and FAQs to identify common questions or recurring issues. Will work together with Solehin for customer inquiries in Telegram Group.
Objective 3: Collaborate with other teams to strengthen Cytron’s capability in 3D Printing, Robotics, and STEM initiatives | KR1: Support cross-team projects and develop demo resources that highlight Cytron’s technical strengths in 3D Printing, Robotics, and STEM areas | 1. Engage with Education, Ecodev, and Marketing teams to identify ongoing or upcoming projects in 3D Printing, Robotics, and STEM.
2. Join relevant events or workshops to gather direct feedback from users and showcase Cytron’s technical strengths
3. Share insights from these activities to help refine future products or content.
Incoming Task/Event 1. Review and test for Creality K2 Pro 3D Printer compared to Bambu Lab P1S 2. Digital Carnival @ SSTP on 2-4 November 3. PISF 2025 on 8-9 November 4. RAC2026 (as comittee) starting Mid October
|  | Next Event if needed 1. Bengkel Asas Sumo Robot 2. 3D Printer Workshop |  | 3D Printer workshop at UniMap

## Gannt Chart Q1
|  | January |  |  |  | February |  |  |  | March
|  | 5hb - 9hb | 12hb - 16hb | 19hb - 23hb | 26hb - 30hb | 2hb - 6hb | 9hb - 13hb | 16hb - 20hb | 23hb - 27hb | 2hb - 6hb | 9hb - 13hb | 16hb - 20hb | 23hb - 27hb | 30hb - 3hb
Objective 1: Take ownership of the Cytron Tutorial platform to ensure it is well-organized, updated, and follow the standard that we set | Structured Industrial Tutorial (100+)
Discover Cytron wiki
Cytron Tutorial Internal Training (Trainees)
Structured Motor Driver Tutorial (30+)
Structured Raspberry Pi Tutorial (200+)
Telegram Automation (Add more Telegram Group)
Structured Robotics Tutorial (40+) - support for Robo Grip & RAC
Structured micro:bit Tutorial (100+)
Structured Arduino Tutorial (150+)
Objective 2: | Raspberry Pi with MDDS30
Robo Grip Example Project
How to choose a suitable DC motor? - re-edit
Peak Current vs Continuous/Rated Current
Objective 3: | RAC26 Internal Game
3D Design Internal Training
Makerlab Setup
Soccer Package